## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | 1 | Foundations required for doing project | MUST HAVE | No Dependency | Sujit Yadav | 3- Completed
S2 | S2 | 2 | LLM for Contract analysis | MUST HAVE | No Dependency | Sujit Yadav | 3- Completed
S3 | S3 | 3 | Clause Identification and Risk Analysis Engine | MUST HAVE | No Dependency | Sujit Yadav | 3- Completed
S4 | S4 | 4 | Update tracking and Contract Modification | MUST HAVE | No Dependency | Sujit Yadav | 3- Completed
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
[9 empty] | Nov 10th | Nov 11th | Nov 12th | Nov 13th | Nov 14th | Nov 15th | Nov 16th | Nov 17th | Nov 18th | Nov 19th | Nov 20th | Nov 21th | Nov 22nd | Nov 23rd
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Sujit Yadav | Learnt and practice all the fundamentals foe the Project | Done |  | Introduction Session | Installation of Python and Jupyter Notebook | Naming Conventions ,Identifier,Rules for Identifers,Keywords | Variables, How to operate on aglile sheet | Understanding types of Data Structures-String, list ,tuple,set ,dict and Types of data | Revision of variables,Identifiers | Revision of Data Structures | Range,Mutable and Immutable data, flow control | python functions | Function with return keyword,Types of Arguments | Python Modules | Object Oriented Programming in python | Constructors and Instance Variable | Revision
2 |  | LLM For Contract Analysis | Nov 25th | Dec 9th | Sujit Yadav | Understood about LLM and executed,project | Done |  | Understanding the Project | Quick Overviews of the team members about what they Understood about the project | Virtual Environment Creation | Introduction of Tech tools | Shared Team members understanding about the Project | Practised Python Concepts | Practised this week topics | Prompt Engineering | Difference between Data Science, AI and Gen AI and also the Fundamentals of LLM | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | Packages and Workflow for next Milestone | Revised and Practised Prompt Engineering | Executed demo codes
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Sujit Yadav | understood clause extraction and risk analysis | Done |  | Nov 10th: Overview of project; Nov 11th: Project Presentation; Nov 12th: how to createVirtual Environment in detail; Nov 13th: Introduction to tech tools; Nov 14th: Presentation of project; Nov 15th: Revised; Nov 16th: Practiced Python Concepts
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Sujit Yadav | Update tracking and contract modification | Done |  | Worked on Assignment | Discussed about Assignment Progress | Learnt about Regulatory update Tracking theoretically | Executed demo1 code and Delivering the Assignment Understanding by team members | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | revised pevious topics | practiced demo codes | contract modification and ammendment | Milestone 3 Revision | Implemented of Milestone 3 codes | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Practised Milestone3
Note on D2: ====== ID#AAABv5noruQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABv6zxceE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABv6zxceM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABv6zxceY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABv6zxceU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABv6zxceA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABv5noruA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABv5noruI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABv6zxcec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABv6zxceI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABv6zxcd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABv6zxcd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABv5noruM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABv5noruU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABv6zxceQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABv5noruE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABv6zxcd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying all potential use cases due to incomplete information. | Conducted additional research and consulted online resources to fill gaps.
Sprint 2 | Day 9 | Confusion about prioritizing use cases for preparation. | Created a priority matrix to evaluate and rank use cases based on importance.
Sprint 3 | Day 12 | Difficulty in debugging Python practice code | Collaborated with Vaibhav and Akshaya to resolve issues
Sprint 4 | Day 16 | SQL queries taking longer than expected | Optimized queries with mentor support
Sprint 5 | Day 23 | Challenges integrating voice processing with workflows | Scheduled team debugging session

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-08 | 2026-01-13 | Sujit Yadav | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2
3
4
5
6
7